## KYPRO Bug Status
Bug ID | Page/Feature | Bug Title | Severity | Original Status | Code Review Status | Notes
KYPRO-2 | Communities / Tag Filter | Show More tag button reveals no additional tags | Medium | New | Fixed | Array slicing implemented: first 5 shown, rest on click via showAllTags toggle in enhanced-list-view.tsx
KYPRO-3 | Communities / Tag Filter | Tag filter treats 'UAT' and 'uat' as separate tags | Low | New | Open | Tags stored case-sensitively. No .toLowerCase() normalization on add or compare.
KYPRO-4 | Communities / Card | Watermarked Shutterstock image as community cover | High | Won't fix | Won't fix | Test community content issue, not a code bug.
KYPRO-5 | Communities / Grid View | Red/pink border glow on content container after Show More | Low | New | Open | No explicit focus state cleanup found. CSS :focus/:active may leak to parent container.
KYPRO-10 | Communities / Card (Grid) | Default placeholder icon bottom-aligned instead of centered | Low | New | Open | Aspect ratio padding-top trick may prevent vertical centering of placeholder icon.
KYPRO-11 | Communities / View Toggle | View mode not persisted after navigating away | Low | New | Open | viewMode stored in React state only. No localStorage persistence.
KYPRO-12 | Communities / Card Tags | +1 tag overflow badge shows no tooltip | Low | New | Open | No title attribute or Tooltip component on overflow badge div.
KYPRO-6 | Create Community / Step 1 | Label and placeholder text overlap in Description/Tagline | Medium | New | Fixed | Textarea sets placeholder=' ' with floating label CSS properly handling empty/unfocused state.
KYPRO-7 | Create Community / Validation | Validation toast clipped behind modal overlay | Medium | New | Needs Testing | Toast z-[100] > modal z-50, but rendering context may clip. Requires visual verification.
KYPRO-8 | Create Community / Buttons | Next/Finish buttons appear visually disabled | Medium | New | Open | Buttons use backgroundColor '#E8DFD1' (light beige) — low contrast with text color '#5B4A3A'.
KYPRO-9 | Create Community / Post-creation | No success notification after creation | Low | New | Fixed | Success toast added: 'Community created successfully.' at line 595.
KYPRO-56 | Create Community / Step 1 | Trailing hyphen in auto-generated handle | Low | New | Fixed | sanitizeHandle() strips trailing hyphens via regex /^-+¦-+$/g.
KYPRO-57 | Create Community / Step 1 | Toggle thumb dark brown/black in OFF state | Low | New | Open | Switch thumb color hardcoded to hsl(var(--primary-foreground)) without checked/unchecked distinction.
KYPRO-58 | Create Community / Plan Limit | Plan limit error only shown after completing form | High | New | Fixed | Plan limit checked in useEffect on dialog open; planLimitReached state blocks creation upfront.
KYPRO-59 | Create Community / Step 2 | Background image upload fails for ~7.5MB jpg | High | New | Needs Testing | Client accepts up to 10MB. Server-side limit or processing error may be the cause.
KYPRO-60 | Create Community / Step 1 | Custom Handle not auto-generated from name | High | New | Fixed | Auto-generation logic at lines 278-300 generates handle when name changes.
KYPRO-61 | Create Community / Navigation | Raw-name URL slug causes app crash | High | New | Fixed | validateHandleComplete() validates all handles; sanitizeHandle() removes invalid chars.
KYPRO-13 | Audience / Add Member | Validation error hidden below fold | Medium | New | Fixed | Form has overflow-y-auto with inline error display.
KYPRO-14 | Audience / Add Member | Invalid email accepted without validation | High | New | Fixed | Email validation checks for '@' character in audience/page.tsx.
KYPRO-15 | Audience / Member Profile | 'Acquired Via: Sign Up' incorrect for manual adds | Low | New | Open | No 'addedManually' flag set in member-dialog.tsx; defaults to 'Sign Up'.
KYPRO-16 | Audience / Member Profile | No Edit button on member profile page | Medium | New | Open | Member profile page has no edit button anywhere.
KYPRO-17 | Audience / Member List | Community owner not in member list; count mismatch | Medium | New | Open | audience/page.tsx explicitly filters out owner and admin roles.
KYPRO-39 | Audience / Add Member | All validation errors hidden below fold | High | New | Fixed | Same fix as KYPRO-13: inline error display with scrollable form.
KYPRO-40 | Audience / Invite Member | Floating label overlaps placeholder in invite modal | High | New | Needs Testing | Uses standard Input components; label styling may still overlap in empty state.
KYPRO-41 | Audience / Invite Member | Email/WhatsApp buttons no default selected state | Medium | New | Open | Both channels default to false (lines 26-27); no pre-selection.
KYPRO-42 | Audience / Invite Member | Email and WhatsApp selectable simultaneously | Medium | New | Open | Code allows both to be true simultaneously — may be intentional design.
KYPRO-43 | Audience / Invite Member | Validation uses native window.alert() | High | New | Open | Multiple alert() calls in invite-member-dialog.tsx (lines 124, 130, 221, 227, 231, 237, 251, 256).
KYPRO-44 | Audience / Invite Member | Modal closes before API response confirmed | Medium | New | Open | Modal closes after 500ms setTimeout without awaiting API response.
KYPRO-45 | Audience / Invite Member | Error exposes Resend provider details | High | New | Open | Backend error message passed directly to alert() — leaks infrastructure info.
KYPRO-46 | Audience / Search | Search extremely slow with page jumps | Medium | New | Needs Testing | Frontend filtering logic looks fine; may be server-side pagination issue.
KYPRO-47 | Audience / Search | 'Deselect All' shown when search returns zero | Low | New | Open | Logic: selectedIds.size === filteredItems.length — true when both are 0.
KYPRO-48 | Audience / Tags | Available tags hidden on initial modal open | Low | New | Open | TagInput only shows unselected tags; timing of availableTags loading may cause issue.
KYPRO-49 | Audience / Tags | No autocomplete suggestions for existing tags | Medium | New | Open | TagInput has basic text input with no autocomplete functionality.
KYPRO-50 | Audience / Select All | Select All only selects currently loaded members | High | New | Open | handleSelectAll uses filteredItems which only includes loaded page (PAGE_SIZE=20).
KYPRO-51 | Audience / Tag Members | X button doesn't close modal | Medium | New | Open | Prop mismatch: tag-members-dialog passes onClose but CustomFormDialog expects onOpenChange.
KYPRO-52 | Audience / Tag Members | Selection state lost after closing modal | High | New | Open | No selection persistence across dialog open/close cycles.
KYPRO-18 | RSVP & Guestlist | Empty Guestlist Name silently accepted | Medium | New | Fixed | Validation added: if (!guestlistName.trim()) shows toast error.
KYPRO-19 | RSVP & Guestlist | 'Guestlist Details' link is dead | High | New | Fixed | Guestlist detail dialog renders correctly; 'Guestlist Details' is now a title, not a dead link.
KYPRO-20 | RSVP & Guestlist | No Send Invitations functionality | High | New | Fixed | 'Send Invitations' button with sendConfirmationEmails() exists on RSVP page.
KYPRO-21 | RSVP & Guestlist | No RSVP status tracking per guest | Medium | New | Fixed | RSVP status badges (accepted/declined/pending) shown per member.
KYPRO-25 | RSVP & Guestlist | Terminology inconsistency: Guestlist vs Event | Low | New | Open | Schedule uses 'Create Event', RSVP uses 'Create RSVP', Guestlist uses 'Create Guestlist'.
KYPRO-22 | Schedule | Empty Event Name silently accepted | Medium | New | Fixed | Validation: if (!eventName.trim()) with error toast.
KYPRO-23 | Schedule | Start/End time fields not marked required | Low | New | Open | Date/time fields have labels without asterisks. Only Event Name and Guestlist have *.
KYPRO-24 | Schedule | Create Event disabled with no feedback | High | New | Open | Button disables but no tooltip/error explains why. Partial time input not handled.
KYPRO-26 | Integrations / Manual Entry | Invalid email accepted in manual import | High | New | Fixed | Email validation with regex check at line 197-201 rejects invalid emails.
KYPRO-27 | Integrations / CSV | Silently accepts unrecognized column headers | High | New | Partially Fixed | validateHeaders warns about unrecognized columns but still proceeds with import.
KYPRO-28 | Integrations / Excel | Excel .xlsx import fails entirely | High | New | Needs Testing | xlsx library used for parsing; code appears functional but needs live test.
KYPRO-29 | Integrations / CSV | Missing required columns accepted silently | High | New | Open | Only requires 'name' OR 'email', not both. Missing columns get empty strings.
KYPRO-30 | Integrations / CSV | Non-comma delimiters corrupt data | High | New | Partially Fixed | detectDelimiter() auto-detects tab vs comma, but may not cover semicolons.
KYPRO-31 | Integrations / CSV | No duplicate detection in CSV import | Medium | New | Open | runImport imports all rows with no dedup check.
KYPRO-32 | Integrations / Excel | No header row consumes first data row | High | New | Open | sheet_to_json with header:1 treats row 1 as headers always.
KYPRO-33 | Integrations / Manual Entry | Contacts accepted without email (name only) | High | New | Open | Only requires 'name OR email' — empty email allowed.
KYPRO-34 | Integrations / Manual Entry | Empty form creates blank null records | High | New | Open | Partial validation: both empty blocked, but edge cases create blank entries.
KYPRO-35 | Integrations / Manual Entry | Enter in Tags field triggers premature import | Medium | New | Open | onKeyDown Enter handler on tags field calls addManualMember() instead of adding tag.
KYPRO-36 | Integrations / Import | Drag & drop file upload non-functional | High | New | Open | No drag-and-drop event handlers found in upload components.
KYPRO-37 | Integrations / Manual Entry | Invalid email accepted in import manual entry | Medium | New | Fixed | Validation at lines 196-201 rejects invalid emails with toast.
KYPRO-38 | Integrations / Manual Entry | No duplicate detection in manual entry | Medium | New | Open | addManualMember adds without checking for existing entries.
KYPRO-62 | Integrations / TSV | Tab delimiter not recognized in TSV import | High | New | Partially Fixed | detectDelimiter exists for tab detection, but may fail in edge cases.
KYPRO-63 | Integrations / Import Preview | Two duplicate import buttons | Low | New | Open | Both 'Import N' (top-right) and 'Import N Members' (bottom-right) present.
KYPRO-64 | Integrations / Manual Entry | Phone field accepts alphabetic characters | Medium | New | Open | No phone format validation on manual entry phone input.
KYPRO-66 | Integrations / Manual Entry | No character length limit on Name/Email | Medium | New | Open | No maxLength attribute on input fields.
KYPRO-67 | Integrations / Manual Entry + Profile | Long name/email causes layout overflow | Medium | New | Open | Table has truncate classes but may overflow in narrow views or profile cards.
KYPRO-53 | Login / Forgot Password | Password reset email lands in spam | Medium | New | Needs Testing | Server-side email config issue (SPF/DKIM/DMARC). Cannot verify from code alone.
KYPRO-54 | Login / Forgot Password | Reset link goes to www.kyozo.com not pro.kyozo.com | High | New | Open | NEXT_PUBLIC_APP_URL defaults to ayvalabs.com; needs proper env config for pro.kyozo.com.
KYPRO-55 | Login / Forgot Password | Forgot password state not cleared on dismiss | Medium | New | Open | Dialog state not reset when X button closes the modal.
KYPRO-65 | Security / Authorization | IDOR: Any authenticated user can access any community | Critical | Fixed | Needs Verification | CSV says Fixed. API routes verify ID token but authorization per community needs live testing.
KYPRO-68 | Security / Authorization | Member-level accounts gain full admin access | Critical | Fixed | Needs Verification | CSV says Fixed. Role enforcement between kyozo.com and pro.kyozo.com needs live testing.

## Summary
Status | Count
Fixed | 17
Open | 38
Partially Fixed | 3
Needs Testing | 6
Needs Verification | 2
Won't fix | 1
Total Bugs | 67